## Sheet1
Project | ABBC GreenPrints Extension | Test Designed By: | Claire Seccombe
Release | 1, 2 & 3 | Test Designed Date: | 2019-10-11
|  | Test Executed By: | Claire Seccombe
Test Case ID | Test Objective | Precondition | Steps | Test Data | Acceptance Criteria | Test Status
Release 1
1 | Bioregion Information |  | 1. Open page 2. Select Bioregion 3. Look at Bioregion information display | N/A | - The regions surround the selected bioregion become less visible / non interactive. - User selects a region and clicks a button to focus on that region. - Extra filters for the selected region should also be optional for the user to select from. | Passed
2 | Sub-bioregion Information |  | 1. Open page 2. Select Sub-bioregion 3. Look at Sub-bioregion information display | N/A | - The regions surrounding the selected sub-bioregion become less visible / non interactive and focuses on that particular sub-bioregion. - Extra filters for the selected region should also be optional for the user to select from. | Passed
3 | Isolate Bioregins |  | 1. Open page 2. Select Bioregion | N/A | - User selects a layer that displays the bioregions and - The selected bioregion has a brief description about the region and its sub-regions. | Passed
4 | Isolate Sub-bioregions |  | 1. Open page 2. Select Sub-bioregion | N/A | - User selects a layer that displays the sub-bioregion - The sub-region selected displays information about the region and links to more information. | Passed
Release 2
5 | Drawing Tool |  |  | Select Drawing Tool Draw on map | - Drawing toolbar is displayed - Isolate my bioregion or bio-subregions of choice - Apply different filters so that I can see different information about land use and other information on the map - Capture a static image of the bioregion, using the filters selected - Be able to draw on the static image of the bioregion and print out the whole map, including what I have drawn and what is still showing from the filters I chose before taking a static capture - User selects a function that has the ability to draw -- vegetation on the map -- new agricultural activities on the map -- residential, commercial and industrial developments on the map -- community spaces on the map (‘commons’) -- fence lines -- water ways, such as rivers, streams, openings between lakes etc | Passed
Release 3 (Dropped)
6 | Bioregion Land Use |  | 1. Open page 2. Select bioregion land use layer | N/A | - User selects a layer that displays agriculture* - User selects a layer that displays forestry. - User selects a layer that displays urban settlements | Dropped
7 | Sub-Bioregion Land Use |  | 1. Open page 2. Select sub-bioregion land use layer | N/A | - User selects a layer that displays agriculture* - User selects a layer that displays forestry. - User selects a layer that displays urban settlements | Dropped
8 | History of Land Use |  | 1. Open page 2. Select history of land use layer | N/A | - User can select a time period and compare it to present day. | Dropped